## Template
Risk Register Template
Number your risks here for reference: 1, 2, 3 etc | The title of the risk, issue, opportunity or action - be concise but clear | If an action, put the number of the risk, issue or opportunity it relates to as per column A | Who has ultimate responsibility for this risk? | Who has responsibility for carrying out this action? | Is the risk open, draft or closed? | Is this a risk, issue, opportunity or action? | Is the action draft, in progress, slipped or complete? | Give your risk an impact from 1 to 5: see customisable scale below | Give your risk a likelihood from 1 to 6, 6 being 'issue': see customisable scale below | Calculated risk rating based on the selected impact and likelihood scores | Are there any departments responsible for managing this risk? | If necessary, put a due date for closing the risk, issue, opportunity or action | How will this risk affect your organisation? E.g. financially, reputationally, operationally… | What strategy will you take to deal with this risk? | Similar and often the same as strategy, what is this action attempting to do? E.g. mitigate, exploit, insure… | Which individual originally identified this risk? | Put in any further required detail here as free text
Item Number | Title | Parent Item | Risk Owner | Action Owner (s) | Risk Status | Type | Action Status | Impact | Likelihood | Rating | Department(s) | Due Date | Impact Type(s) | Strategy | Action Type | Identified By | Description
1 | Heavy rain on event day causing delay to show |  | John Smith |  | Open | Risk |  | 3 | 4 |  | Event Operations | 26/06/2021 | Operational | Mitigate |  | Jane Smith
| Set up marquees | 1 |  | Jane Smith |  | Action | In Progress |  |  |  |  | 25/06/2021 |  |  | Mitigate |  | Contacting supplier Mike's Marquees
| Provide staff with branded raincoats | 1 |  | John Smith |  | Action | In Progress |  |  |  |  | 2021-06-25 |  |  | Mitigate |  | Contacting supplier Anne's Anoraks
2 | Road closure just outside town centre |  | Jane Smith |  | Draft | Issue |  | 4 | 6 |  | Transport and Travel | 2021-06-26 | Operational | Contingency |  | Angela Abar
| Delay start of event by 30 minutes | 2 |  | Jane Smith |  | Action | In Progress |  |  |  |  | 2021-06-26 |  |  | Contingency |  | Daily run sheet updated with 30 minute delay applied to all items
3 | Cyber attack during next Olympic Games |  | Jane Smith |  | Open | Risk |  | 5 | 2 |  | Technology | 2024-05-15 | Reputational, Security, Operational | Mitigate |  | John Smith
| Strengthen techology systems | 3 |  | John Smith |  | Action | Draft |  |  |  |  | 2024-01-01 |  |  | Mitigate |  | Research lines of defence and hire consultants
| Back-up system in place | 3 |  | Jane Smith |  | Action | Draft |  |  |  |  | 2024-05-15 |  |  | Contingency |  | Fall-back system available at any time
4 | Volunteer takes too long a lunch break |  | John Smith |  | Open | Risk |  | 1 | 1 |  | Workforce Management | 2021-04-18 | Operational | Accept |  | Jane Smith
| Let them have their break! | 4 |  | Jane Smith |  | Action | Draft |  |  |  |  | 2021-04-18 |  |  | Accept |  | This is not a good risk John!
Impact |  |  | Likelihood |  |  | Matrix
6
Score | Label |  | Score | Label |  |  | 5
1 | Minimal |  | 1 | Highly Unlikely |  |  | 4
2 | Minor |  | 2 | Unlikely |  | Likelihood | 3
3 | Moderate |  | 3 | Possible |  |  | 2
4 | Major |  | 4 | Likely |  |  | 1
5 | Extreme |  | 5 | Highly Likely |  |  |  | 1 | 2 | 3 | 4 | 5
|  |  | 6 | Issue | [5 empty] | Impact
Uncertainty Type
It is important to understand the difference between different types of uncertainty so that you can manage each one effectively.
Risk | A risk is something unplanned that might happen that could have a negative impact on your event.
Issue | An issue is something that is currently happening and is having a negative impact on your event.
Opportunity | An opportunity is something unplanned that might happen that you could exploit to have a positive impact on your event.
Risk Strategy
A key difference between risks, issues and opportunities is the strategy you deploy to address each item type. Here is a list of the strategies you might employ to deal with uncertainty.
Mitigate | A mitigation plan is a series of actions that you take in advance of a potential event that reduces the likelihood and / or impact of that event.
Contingency | A contingency plan will identify the likely actions needed to resolve a potential issue, including who is responsible for enacting them. The plan will be actioned if the issue does actually occur.
Exploit | Opportunities arise when you have the chance to benefit from an uncertainty. It is therefore wise to pursue a strategy that allows you to make the most of the opportunity for your positive gain.
Avoid | This involves removing the risk entirely, in taking some action that results in the uncertainty no longer posing the same threat to your event that it previously did.
Insure | This strategy might apply when you are able to take out some sort of insurance that eases the impact of the risk becoming an issue. It allows you to pass the risk onto a third party.
Share | This lets you spread the risk or opportunity amongst a supply chain, taking actions that acknowledge that this is a risk that is not solely up to you to deal with and that is not solely yours to be harmed by.
Accept | A risk can be accepted after all other viable strategies such as mitigation, avoidance or insurance have been enacted; the risk still exists, but there is an acceptance that no more action can be taken to manage it.