## Template
Task Management Template
Number your tasks here for reference: 1, 2, 3 etc | The title of the task or sub-task - be concise but clear | The larger piece of work within which the task sits | (Optional) If you wish to group similar tasks within a project, put the name of the task group here | If a sub-task, put the number of the task it relates to as per column A | Give your task a RAG rating of Grey, Red, Amber, Green, or Blue: see scale below | Put a date on which work on the task should begin | Put a date by which the task should have been completed | The department(s) responsible for managing this task | The individual(s) responsible for managing this task | Any individuals that need to be kept up to date on the progress of the task, despite not having ultimate responsibility for it | Give your important tasks a milestone type of Gold, Silver and Bronze. See below for more on milestones | Put in any further required detail here as free text | Record original start and due dates here to track the timeline of a task from creation to completion |  | If you want to track task progress in a more granular way, put % values of 0, 25, 50, 75 or 100 in here
Item Number | Title | Project | Task Group | Parent | RAG Status | Start Date | Due Date | Department (s) | Owner (s) | Subscriber (s) | Milestone Type | Description | Baseline Start Date | Baseline Due Date | % Complete
1 | Create social media calendar | Marketing Plan 2021 | Social Media |  | Blue | 2021-01-01 | 2021-01-31 | Marketing | Jane Smith | John Smith |  | Use Excel for this
2 | Research social media management tool | Marketing Plan 2021 | Social Media |  | Green | 2021-03-15 | 2021-04-15 | Marketing | Jane Smith
3 | Social Media Management Tool | Marketing Plan 2021 | Social Media |  | Green | 2021-04-16 | 2021-04-20 | Marketing | Jane Smith
| Begin social media management tool subscription | Marketing Plan 2021 | Social Media | 3 | Green | 2021-04-16 | 2021-04-16 | Marketing | Jane Smith
| Send invoice to finance | Marketing Plan 2021 | Social Media | 3 | Grey | 2021-04-17 | 2021-04-20 | Marketing; Finance | Jane Smith
4 | Confirm KPIs for social media for 2021 | Marketing Plan 2021 | Social Media |  | Amber | 2021-02-26 | 2021-02-26 | Marketing; Business Development | Jane Smith |  | Silver
5 | Undertake website review | Marketing Plan 2021 | Website |  | Blue | 2021-01-01 | 2021-01-31 | Marketing | Jane Smith
6 | Create new webpages | Marketing Plan 2021 | Website |  | Grey | 2021-05-01 | 2021-06-01 | Marketing | John Smith
7 | Confirm KPIs for website for 2021 | Marketing Plan 2021 | Website |  | Red | 2021-02-26 | 2021-02-26 | Marketing; Business Development | John Smith |  | Silver
8 | Produce white paper on productivity | Marketing Plan 2021 | White Papers |  | Grey | 2021-04-01 | 2021-06-30 | Marketing | John Smith
9 | Produce white paper on remote working | Marketing Plan 2021 | White Papers |  | Grey | 2021-07-01 | 2021-09-30 | Marketing | John Smith | Jane Smith
10 | Produce white paper on economy | Marketing Plan 2021 | White Papers |  | Grey | 2021-10-01 | 2021-12-30 | Marketing | John Smith | Jane Smith
| Plan content | Marketing Plan 2021 | White Papers | 10 | Grey | 2021-10-01 | 2021-11-01 | Marketing | John Smith
| Research statistics | Marketing Plan 2021 | White Papers | 10 | Grey | 2021-10-01 | 2021-11-01 | Marketing | John Smith
| Compile paper | Marketing Plan 2021 | White Papers | 10 | Grey | 2021-11-02 | 2021-12-15 | Marketing | John Smith
| Publish and publicise | Marketing Plan 2021 | White Papers | 10 | Grey | 2021-12-18 | 2021-12-30 | Marketing | John Smith
Task Management: The Basics
Projects contain Tasks which need to be carried out in order for the project to be complete. A project is a distinct set of work with an achievable endpoint; a task is a basic unit of work.
Similar tasks can be grouped into Task Groups within a project, or they can be divided into smaller Sub-Tasks which all contribute towards the completion of the task.
Tasks and sub-tasks are then assigned to Departments and Owners, who are those doing the work.
RAG Status
This is the coloured system indicating task progress. WeTrack uses the following scale: |  |  |  | Not Started: work has not yet started on this item.
Overdue / Issues: behind schedule or below required standard.
Slipping / No Progress: falling behind or has not started on time.
On Track: in progress and on track for completion.
Complete: completed to required standard.
Milestones
Milestones are a type of task that have an added level of significance. Milestones have the same start and due date and, as such, are used to denote key days in your project's progress.
Tasks and milestones are used together to create your project schedule. You might have a series of tasks that lead into a milestone: once all the tasks are completed, the milestone is achieved.
In WeTrack, there are three customisable levels of milestone, allowing you to monitor and report on milestones at the right level.
The default milestones in WeTrack are Gold, Silver and Bronze:
Gold
Silver
Bronze